## Project Overview
WFS PROJECT OVERVIEW
Field | Value | Status | Notes
Project Name | WFS (Workforce Solutions) | Active | Intuit HCM Platform
Client | Intuit | Active | QuickBooks Online
TestBox Lead | Katherine Lu | Active | Program Lead
TSA Assigned | Thiago Rodrigues | Active | Technical Solutions Architect
TSA Lead | Lucas Wakigawa (Waki) | Active | Team Lead
Alpha Access Date | December 12, 2025 | DONE | GoQuick Alpha Retail
SOW Target Date | December 19, 2025 | IN PROGRESS | Today!
WFS Alpha Launch | December 2025 | Upcoming | ~100 customers
WFS Beta Launch | February 2026 | Planned | Early Access Feb 4
WFS GA Launch | May 1, 2026 | Planned | Full launch
Exploration Environment | GoQuick Alpha Retail | DONE | Realm ID: 9341455848423964
Mineral HR Access | Confirmed via SSO | DONE | PR_ELITE billing plan
QBO Routes Mapped | 47 routes | DONE | 100% functional
WFS Reports Identified | 27 reports | DONE | All with URLs
Screenshots Captured | 54+ screenshots | DONE | QBO + Mineral

## Timeline
Phase | Milestone | Target Date | Status | Owner | Dependencies
Exploration | Alpha Access Granted | Dec 12, 2025 | DONE | Intuit | None
Exploration | QBO Complete Mapping | Dec 19, 2025 | DONE | Thiago | Alpha Access
Exploration | Mineral HR Mapping | Dec 19, 2025 | DONE | Thiago | Alpha Access
Exploration | Intuit Intelligence Discovery | Dec 19, 2025 | DONE | Thiago | Alpha Access
SOW | SOW Draft Complete | Dec 19, 2025 | IN PROGRESS | Thiago/Katherine | Exploration
SOW | Internal Review | Dec 20, 2025 | Pending | Katherine | SOW Draft
SOW | SOW to Client | Dec 23, 2025 | Pending | Katherine | Internal Review
SOW | SOW Approval | Jan 6, 2026 | Pending | Intuit | SOW to Client
Winter Release | Feature Analysis | Dec 22, 2025 | Pending | Thiago/Waki | Doc Access
Winter Release | Early Access | Feb 4, 2026 | Planned | Intuit | SOW Approval
Alpha | Wave 1 Build Start | Jan 13, 2026 | Planned | Thiago | SOW Approval
Alpha | Demo Stories Ready | Jan 27, 2026 | Planned | Thiago | Wave 1 Build
Alpha | Health Checks Automated | Feb 3, 2026 | Planned | Thiago | Demo Stories
Beta | Wave 2 Build Start | Feb 10, 2026 | Planned | Thiago | Alpha Complete
Beta | Enhanced Data Ready | Mar 3, 2026 | Planned | Thiago | Wave 2 Build
GA | Wave 3 Build Start | Apr 7, 2026 | Planned | Thiago | Beta Complete
GA | Production Ready | May 1, 2026 | Planned | Team | Wave 3 Build

## Action Items
Priority | Action Item | Owner | Due Date | Status | Blocker? | Notes
P0 | Finalize SOW draft with Mineral scope | Thiago | Dec 19 | In Progress | No | Include Mineral HR integration
P0 | Review Winter Release doc (24 features) | Thiago/Waki | Dec 22 | Pending | No | Identify data/automation needs
P0 | Share SOW internally for review | Thiago | Dec 20 | Pending | No | Get Katherine's feedback
P1 | Follow-up with Kev about click path | Katherine | Dec 23 | Pending | Yes | Blocking demo planning
P1 | Document Winter Release matrix | Thiago | Dec 22 | Pending | No | Feature vs effort analysis
P1 | Confirm final demo environment | Katherine | Jan 6 | Pending | No | GoQuick is temporary
P1 | Request PRDs from Intuit | Katherine | Jan 6 | Pending | Yes | Main blocker for scope
P2 | Test employee creation via UI | Thiago | Jan 13 | Pending | No | Part of Wave 1
P2 | Test time entry creation via UI | Thiago | Jan 13 | Pending | No | Part of Wave 1
P2 | Setup automated health checks | Thiago | Jan 27 | Pending | No | Daily automation
P2 | Validate demo stories with Intuit | Katherine | Jan 27 | Pending | No | Before Beta
P3 | Document Mineral API (if available) | Thiago | Feb 10 | Pending | No | Contact Mitratech if needed
P3 | Create enablement documentation | Thiago | Apr 28 | Pending | No | For GA launch

## Risks
ID | Risk | Probability | Impact | Severity | Mitigation | Owner | Status
R1 | PRDs not received from Intuit | Medium | High | HIGH | Modular SOW that can be refined | Katherine | Open
R2 | Final demo environment different from Alpha | High | Medium | HIGH | Document transition plan | Katherine | Open
R3 | Click path for reps undefined | High | High | CRITICAL | Follow-up with Kev urgently | Katherine | Open
R4 | Mineral integration details TBD | High | Medium | HIGH | Separate scope for Mineral | Thiago | Open
R5 | Winter Release overlap with WFS | High | Medium | HIGH | Plan capacity early | Waki | Open
R6 | Staged rollout impacts all sellers | Medium | High | HIGH | Careful implementation plan | Katherine | Open
R7 | License count unclear for Feb | Medium | Low | MEDIUM | Confirm with Christina | Katherine | Open
R8 | SOW deadline missed | Low | High | MEDIUM | Finalize today | Thiago | In Progress

## Data Architecture
Component | Type | Source | Target | Data Flow | Status | Notes
Employee ID | Golden Thread | QBO Payroll | All Modules | Bidirectional | Confirmed | Links employee across system
Time Entries | Transactional | Time Module | Payroll/Projects | One-way | Confirmed | Flows to paycheck
PTO Requests | Transactional | Time Off | Payroll | One-way | Confirmed | Affects pay calculation
Job Costing | Analytical | Projects | Reports | Aggregated | Confirmed | For profitability analysis
Payroll Data | Master | Payroll | Reports/Tax | One-way | Confirmed | Core HR data
Worker Profile | Master | Employees | All Modules | Reference | Confirmed | Central employee record
Mineral HR Data | External | QBO | Mineral | SSO + Data | Partial | Need click path from Kev
Org Chart | Structural | Employees | Directory | Hierarchical | Confirmed | Shows reporting structure
Documents | Content | Team Module | Employees | Association | Confirmed | Employee documents
Benefits | Master | Team Module | Payroll | Reference | Confirmed | Deductions setup
Workers Comp | Compliance | Team Module | Reports | Calculated | Confirmed | State-specific

## Communications
Context | Recipient | Channel | Urgency | Suggested Message (English) | Notes
PRD Follow-up | Katherine | Slack DM | High | Hey Katherine, quick check on the PRDs from Intuit. Do we have any update on when we might get them? I want to make sure our SOW scope is as accurate as possible. Let me know if there's anything I can do to help move this along. | Main blocker
Click Path Question | Kev (via Katherine) | Slack Channel | High | Hey Kev, following up on my earlier question. We got Mineral access working through QBO and everything looks good on our side. Just wanted to check - what's the click path that sales reps should follow to show data flowing from WFS into Mineral during demos? And what data should we expect to see in Mineral to prove the connection is working? Thanks! | Blocking demo planning
SOW Internal Review | Katherine | Slack DM | High | Hi Katherine, I just finished the SOW draft with the Mineral scope included. Can you take a look when you have a chance? I tried to keep it modular so we can easily update it once we get the PRDs. Let me know if anything needs changes. | Before holiday
Winter Release Analysis | Katherine/Waki | Slack Channel | Medium | Hey team, I'm starting to look at the Winter Release features doc. I'll create a matrix showing which features need new data or automations vs what we already have. Should have something ready by end of day tomorrow. Any specific features you want me to prioritize? | Before Dec 22
Environment Confirmation | Katherine (for Christina) | Slack DM | Medium | Hey Katherine, quick question about the demo environment. I know GoQuick Alpha Retail is just for our exploration. Do we have any update on what the final demo environment will be for sales? Want to make sure we plan the transition properly. | Important for Wave 1
License Count | Katherine | Slack DM | Low | Hi Katherine, when you get a chance, could you check with Christina about the exact number of licenses we'll have for February? I saw the PO mentions 60 additional, just want to confirm for our planning. | Non-urgent
Weekly Status Update | Katherine/Team | Slack Channel | Medium | Weekly WFS Update: Status: On Track Done this week: - Completed QBO exploration (47 routes mapped) - Confirmed Mineral HR access via SSO - Identified 27 WFS-related reports - Discovered Intuit Intelligence (AI BETA) - Captured 54+ screenshots In Progress: - Finalizing SOW draft - Reviewing Winter Release features Blockers: - PRDs still pending - Click path for demos TBD Next Week: - Share SOW for internal review - Complete Winter Release analysis | Template for weekly updates
Exploration Complete | Katherine | Slack DM | Medium | Good news! I finished the full exploration of both QBO and Mineral. Here's what we have: - 47 QBO routes mapped and working - 27 WFS reports identified with direct URLs - Mineral HR fully accessible via SSO - Found Intuit Intelligence (their AI assistant) in beta - 54+ screenshots captured All documented and ready for the SOW. Let me know if you need anything else! | Milestone communication
Kev Introduction | Kev | Slack DM | Low | Hey Kev, I'm Thiago from the TestBox team working on the WFS demo environments. Katherine mentioned you're the go-to person for Mineral integration questions. Would love to connect when you have a few minutes to chat about the data flow between WFS and Mineral. No rush, just whenever works for you. | If direct contact needed
SOW to Client | Katherine (for Intuit) | Email draft | High | Subject: WFS Demo Environment SOW - Ready for Review Hi team, Attached is the Statement of Work for the WFS demo environment build. Key highlights: - Wave 1 (Alpha): Demo environment setup, baseline data, 2 demo stories - Wave 2 (Beta): Enhanced data, additional demo stories, automation - Wave 3 (GA): Production reliability, monitoring, scale testing Assumptions and open items are documented in Section X. We'll refine the scope once we receive the PRDs. Please let us know if you have any questions or need clarification on anything. Best, [Name] | For Katherine to send

## Environment Mapping
Environment | Realm ID | Purpose | Access | Features | Status | Notes
GoQuick Alpha Retail | 9341455848423964 | Exploration Only | Thiago, Katherine, Saubhagya | Full WFS, Mineral, AI | Active | NOT final demo env
Keystone Construction | TBD | Demo Stories | TBD | Job Costing, PTO | Planned | Better for demos
Final Demo Env | TBD | Sales Demos | All reps | Full WFS | TBD | Need confirmation
Mineral HR | Via SSO | HR Compliance | Client Admins | Templates, Training, Tools | Active | PR_ELITE plan

## WFS Reports
Category | Report Name | URL Path | WFS Relevance | Demo Story
Time | Unbilled Time | /app/report/builder?token=UNBILLED_TIME | High | Job Costing
Time | Time Activities by Customer | /app/report/builder?token=TIME_ACTIVITIES_BY_CUST | High | Job Costing
Time | Time Activities by Employee | /app/report/builder?token=TIME_ACTIVITIES | High | Payroll Lifecycle
Time | Recent Time Activities | /app/report/builder?token=RECENT_TIME_ACTIVITIES | Medium | Time Tracking
Time | Project Profitability | /app/reportv2?rptId=PROJECT_PROFITABILITY_SUMMARY | High | Job Costing
Employee | Employee Contact List | /app/report/builder | High | HR Management
Employee | Employee Directory | /app/payroll/reports/employee-directory | High | HR Management
Employee | Employee Details | /app/payroll/reports/employee-details | High | HR Management
Payroll | Payroll Summary | /app/payroll/reports/payroll-summary | High | Payroll Lifecycle
Payroll | Payroll by Employee | /app/payroll/reports/payroll-summary?name=pse | High | Payroll Lifecycle
Payroll | Payroll Details | /app/payroll/reports/payroll-summary?name=details | High | Payroll Lifecycle
Payroll | Paycheck History | /app/payroll/reports/paycheck-history | High | Payroll Lifecycle
Payroll | Deductions/Contributions | /app/payroll/reports/deductions-contributions | Medium | Benefits
Payroll | Payroll Item List | /app/payroll/reports/payroll-item-list | Medium | Setup
Payroll | Total Payroll Cost | /app/payroll/reports/total-payroll-cost | High | Cost Analysis
Payroll | Total Pay | /app/payroll/reports/total-pay | High | Cost Analysis
Tax | Tax Liability | /app/payroll/reports/tax-liability | Medium | Compliance
Tax | Tax Payments | /app/payroll/reports/tax-payments | Medium | Compliance
Tax | Tax and Wage Summary | /app/payroll/reports/tax-wage-summary | Medium | Compliance
Benefits | Vacation and Sick Leave | /app/payroll/reports/vacation-sick-leave | High | Unified PTO
Benefits | Retirement Plans | /app/payroll/reports/retirement-plans | Medium | Benefits
Benefits | State Mandated Retirement | /app/payroll/reports/retirement-plans?name=statemandretplans | Low | Compliance
Compliance | Workers Compensation | /app/payroll/reports/workers-compensation | Medium | Compliance
Compliance | Multiple Worksites | /app/payroll/reports/multiple-worksite | Low | Compliance
Contractor | 1099 Balance Detail | /app/report/builder?SubToken=contractorBalanceDetail | Medium | Contractors
Contractor | 1099 Balance Summary | /app/report/builder?SubToken=contractorBalanceSummary | Medium | Contractors
Contractor | Contractor Payments | /app/payroll/reports/contractor-payments | Medium | Contractors

## Metrics KPIs
Phase | Metric | Target | Current | Status | Measurement
Alpha | SOW Approved | Yes | In Progress | On Track | Client sign-off
Alpha | Environment Mapped | 100% | 100% | DONE | 47/47 routes
Alpha | Demo Stories Ready | 2+ | 0 | Pending | Unified PTO, Magic Docs
Alpha | Health Check Automated | Yes | No | Pending | Daily script running
Beta | Demo Stories Ready | 4+ | 0 | Planned | Add Job Costing, Hire to Fire
Beta | Data Refresh Automated | Yes | No | Planned | Weekly refresh
Beta | Mineral Integration | Documented | Partial | In Progress | Need click path
Beta | Winter Release Features | Incorporated | Pending | Planned | 24 features analyzed
GA | Demo Stories Ready | 6+ | 0 | Planned | Full suite
GA | Production Monitoring | Yes | No | Planned | Alerts configured
GA | Scale Test | Passed | Not Started | Planned | Multiple instances
GA | Enablement Docs | Complete | Not Started | Planned | Training materials